## Gates
MatriSathi stage gates
Day 1 = agreed kickoff. Counts do not approve gates. Amber cells require human input.
Version 1.1: detailed build requirements are in Functional Specs and Technical Specs. Gate IDs SG0–SG7 are milestones; F/T IDs are specs; R IDs are shared requirements.
Gate | Day | Milestone | Demonstrate | Exit criteria | Required reviewers | Evidence pack | Outcome | Decision by / date | Evidence link | Tasks | Verified done | Functional spec IDs | Technical spec IDs
SG0 | 2 | Kickoff and working agreement | Baseline, roles, capacity, repository workflow and clinical owners agreed. | Approve scope amendments, decision owners, weekly hours and first slice. Repository setup evidenced or a named blocker recorded. | Team lead + Tech lead | Baseline files; decision log; owner list; approved next-stage scope. | Pending |  |  |  |  | F001 | T001
SG1 | 7 | Independent foundation | Browser login, mother registration and pregnancy creation survive reload/restart. | AT01–AT05 pass; two organizations tested; clean setup and CI evidence; first slice reviewed. | Tech lead + Team lead | Commit SHA; CI output; synthetic browser demo; schema/permission review. | Pending |  |  |  |  | F002–F004 | T002–T007
SG2 | 14 | Pregnancy care and next actions | Approved ANC plan, birth preparation, tasks, private records and safe patient access work. | AT06–AT10 and AT28 pass; doctor validates journey and schedule; uploaded report is not marked reviewed. | Team lead + Doctor + Tech lead | Clinical version approvals; task/referral demo; private-file access tests. | Pending |  |  |  |  | F005–F015, F044 | T008–T010
SG3 | 21 | Real WhatsApp and voice | Actual outbound template plus inbound text, audio and photo reach a staffed test inbox. | AT11–AT14 pass on consenting staff test numbers; retries, opt-out and recipient ambiguity demonstrated. | Tech lead + Team lead + Doctor | Provider configuration record without secrets; message IDs/statuses; audio demo; failure rehearsal. | Pending |  |  |  |  | F016–F020 | T011–T013
SG4 | 28 | Birth and early postpartum | Separate mother/baby events, twins, discharge, loss pause and transfer work. | AT15–AT18 and AT29 pass; maternal and pediatric reviewers validate event handling. | Doctor + Pediatric reviewer + Tech lead | Twin/loss/transfer scenarios; clinical approvals; task handover evidence. | Pending |  |  |  |  | F021–F028 | T014–T015
SG5 | 42 | Complete MVP scope | All eight journey stages and R01–R12 functionality implemented; release hardening continues. | AT01–AT23 and AT28–AT32 pass; all 12 audio topics approved; all mandatory scope mapped. | Team lead + Doctor/Pediatric reviewer + Tech lead | Traceability matrix; full journey demo; regression; content approvals; open-defect list. | Pending |  |  |  |  | F029–F040 | T016–T020
SG6 | 49 | Field validation and resilience | Representative rural/semi-urban users complete core tasks; restore and failure drills run. | AT24–AT27 pass; at least 5/6 users succeed with intended assistance and no safety-critical misunderstanding. | Team lead + Tech lead + Tester + Doctor | Observed user results; measured load/network report; restore/rollback evidence; retests. | Pending |  |  |  |  | F041–F042 | T021–T022
SG7 | 56 | Pilot-deployable release | Release candidate has complete evidence, operating owners and a reproducible deployment. | AT01–AT32 pass for candidate or valid unchanged evidence; no critical/high defects; three separate sign-offs. | Team lead + Tech lead + Doctor/Pediatric reviewer + Facility owner | Release SHA; checks and approvals; runbooks; roster; rollout/rollback and cost limits. | Pending |  |  |  |  | F043 | T023

## Tasks
MatriSathi task backlog
Version 1.0 ¦ Estimates in hours. Issues/PRs own daily status; refresh this snapshot weekly.
F IDs are detailed in Functional Specs; T IDs in Technical Specs. Filter by Gate or linked task. Existing hours and status fields are unchanged.
ID | Week | Gate | Owner | Est. hours | Task | Dependencies | Requirements | Acceptance / evidence needed | Reviewer | Status | Evidence link | Review result | Actual hours | Issue / PR | Actual reviewer | Verified done | Detailed spec IDs
M001 | 1 | SG0 | Team lead | 3 | Confirm baseline, capacity and pilot setting | None | R09 R11 R12 | Named owners; exact developer hours; two settings and language selected; amendments accepted. | Tech lead | Not started |  | Pending |  |  |  |  | F001, T001
M002 | 1 | SG0 | Tech lead | 2 | Shared repository and engineering agreement | M001 | R09 R10 | Correct remote; protected-main proposal; task branches and approvals documented; secrets ignored. | Team lead | Not started |  | Pending |  |  |  |  | F001, T001, T007
M003 | 1 | SG1 | Tech lead | 6 | Review identity, auth, tenant and audit design | M002 | R02 R07 | Unique staff login, org authority, session revocation and DB-role boundaries specified; AT01–AT04 design approved. | Team lead | Not started |  | Pending |  |  |  |  | F003, F004, T002, T003, T004, T005, T006
M004 | 1 | SG1 | Developer | 7 | Scaffold API, database and first migration | M002 | R02 R09 | Clean local setup; Organization/Facility/Membership/Person/Contact/Episode migrations work. | Tech lead | Review | docs/delivery/evidence/SG1/report.md | Pending |  |  |  |  | F002, T001, T002, T003, T007
M005 | 1 | SG1 | Developer | 8 | Implement staff login and scoped identity endpoints | M003 M004 | R02 R07 | AT01–AT04 pass including existing-person link denial and restricted audit writes. | Tech lead | Review | docs/delivery/evidence/SG1/report.md | Pending |  |  |  |  | F002, F003, F004, F037, T002, T003, T004, T005, T006
M006 | 1 | SG1 | Developer | 7 | Build registration UI and continuous checks | M005 | R09 R10 | Browser login/register/create/view works; CI configured and run after authorized push; AT05 pass. | Tech lead | Review | docs/delivery/evidence/SG1/report.md | Pending |  |  |  |  | F002, F003, T001, T007
M007 | 1 | SG1 | Team lead | 4 | Coordinate reviewer, language and messaging onboarding | M001 | R01 R06 R11 | Provider comparison assigned; staff test numbers and account owner ready; content responsibilities assigned. | Doctor | Not started |  | Pending |  |  |  |  | F016
M008 | 1 | SG1 | Doctor | 2 | Validate intake, roles and journey coverage | M001 | Stages 1–8 R02 R05 | Review notes identify required intake, role limits and pediatric reviewer. | Team lead | Not started |  | Pending |  |  |  |  | F002, F004
M009 | 2 | SG2 | Tech lead | 5 | Review plan/task states and private media controls | M003 | R03 R05 R07 | State-specific permissions, versioned plan rules and private upload/download contract agreed. | Doctor | Not started |  | Pending |  |  |  |  | F005, F007, F008, F009, T002, T008, T009
M010 | 2 | SG2 | Tech lead | 3 | Approve patient/caregiver access mechanism | M003 | R02 R07 | Shared-phone identity confirmation and revocation design reviewed; tests defined. | Team lead | Not started |  | Pending |  |  |  |  | F015, T005, T010
M011 | 2 | SG2 | Developer | 8 | ANC plan, appointments and owned tasks | M005 M009 | Stages 1–3 R03 R05 | AT06 AT07 pass; next action and missed/rescheduled appointment demo works. | Tech lead | Not started |  | Pending |  |  |  |  | F005, F006, F007, F008, T008
M012 | 2 | SG2 | Developer | 8 | Reports, prescriptions and referral tracking | M009 M011 | Stage 2 R03 R07 | AT08 AT09 pass; original records retained; clinical review restricted. | Tech lead | Not started |  | Pending |  |  |  |  | F009, F010, F011, F012, F044, T008, T009
M013 | 2 | SG2 | Developer | 7 | Patient next-action view and birth-plan screen | M010 M011 | Stage 3 R02 R06 | AT10 AT28 pass; caregiver revoke blocks access; no-phone route usable. | Tech lead | Not started |  | Pending |  |  |  |  | F006, F013, F014, F015, F044, T010
M014 | 2 | SG2 | Team lead | 6 | Secure channel approval and prepare clinical content | M007 | R01 R06 R11 | Provider decision/budget and account/template submission recorded; scripts prepared for review. | Doctor | Not started |  | Pending |  |  |  |  | F017
M015 | 2 | SG2 | Doctor | 2 | Approve pilot ANC template and urgent wording | M008 M011 | R05 R06 | Versioned schedule, birth contacts wording and role limits approved or corrections assigned. | Team lead | Not started |  | Pending |  |  |  |  | F005, F012, F013, F014, F044
M016 | 2 | SG2 | Tester | 4 | Test foundation and antenatal slice | M006 M013 | AT01–AT10 AT28 | Repeatable synthetic cases; failures logged with reproduction and evidence. | Tech lead | Not started |  | Pending |  |  |  |  | F007, F009, F011, F015
M017 | 3 | SG3 | Tech lead | 5 | Channel adapter, webhook and outbox design review | M014 | R01 R10 | Authenticated webhook, durable send, dedup/retry and ambiguous-send contracts agreed; failure cases specified. | Team lead | Not started |  | Pending |  |  |  |  | F017, T011, T012
M018 | 3 | SG3 | Tech lead | 3 | Review media/privacy and inbox access | M017 | R01 R02 R07 | Restricted queue, logging, media limits and patient-link authorization designed; access tests specified. | Team lead | Not started |  | Pending |  |  |  |  | F018, F019, T005, T009, T011, T013
M019 | 3 | SG3 | Developer | 8 | Real WhatsApp outbound and callbacks | M017 | R01 R10 | AT11 AT12 pass using staff numbers; delivered/failed/unknown remain distinct. | Tech lead | Not started |  | Pending |  |  |  |  | F016, F017, T011, T012
M020 | 3 | SG3 | Developer | 8 | Staff inbox for text, voice and photo | M018 M019 | R01 R03 | AT13 pass; ownership, backup, original audio playback and manual linking demonstrated. | Tech lead | Not started |  | Pending |  |  |  |  | F018, F019, T009, T011, T013
M021 | 3 | SG3 | Developer | 7 | Approved audio, preferences and fallback | M013 M019 | R01 R06 | AT14 pass; reviewed audio plays through web and permitted WhatsApp route; opt-out enforced. | Doctor | Not started |  | Pending |  |  |  |  | F010, F016, F019, F020, T013
M022 | 3 | SG3 | Team lead | 6 | Run messaging demonstration and support rehearsal | M019 M020 | R01 R11 | Account costs, safe contact preferences and inbox response hours recorded; real channel evidence collected. | Tech lead | Not started |  | Pending |  |  |  |  | F014, F016, T013
M023 | 3 | SG3 | Doctor | 2 | Review audio/templates and clinical routing | M015 M021 | R01 R06 | Initial audio batch and urgent route approved; no automated reassurance. | Team lead | Not started |  | Pending |  |  |  |  | F020
M024 | 3 | SG3 | Tester | 4 | Exercise real channel and failure paths | M019 M020 M021 | AT11–AT14 | Duplicate webhook, failure, opt-out, shared-phone ambiguity and unsupported file tests recorded. | Tech lead | Not started |  | Pending |  |  |  |  | F017, F018, T011
M025 | 4 | SG4 | Tech lead | 5 | Review birth/outcome and child data integrity | M003 | Stages 4–6 R02 R04 | Per-child outcomes; unknown history; independent maternal/child lifecycle and constraints agreed. | Pediatric reviewer | Not started |  | Pending |  |  |  |  | F021, F022, T014
M026 | 4 | SG4 | Tech lead | 4 | Design message pause and transfer concurrency | M017 M025 | R04 R10 | Send-time pause, in-flight limits, ownership handover and sibling separation specified for AT17/AT18. | Doctor | Not started |  | Pending |  |  |  |  | F026, F027, T015
M027 | 4 | SG4 | Developer | 8 | Birth, child linking and separate discharge | M025 | Stages 4–5 R02 R04 | AT15 AT16 AT29 pass; twins and existing child with incomplete pregnancy history work. | Tech lead | Not started |  | Pending |  |  |  |  | F021, F022, F023, T014
M028 | 4 | SG4 | Developer | 8 | Loss pause, transfer and readmission | M026 M027 | R04 | AT17 AT18 pass; maternal support retained; unresolved tasks have receiving owner. | Tech lead | Not started |  | Pending |  |  |  |  | F011, F026, F027, F028, T015
M029 | 4 | SG4 | Developer | 6 | Postpartum and newborn follow-up views | M011 M027 | Stage 6 R03 R05 | Separate plans, missed-contact work and sensitive concern routing demonstrate correctly. | Doctor | Not started |  | Pending |  |  |  |  | F008, F023, F024, F025, F028, T014
M030 | 4 | SG4 | Team lead | 6 | Prepare rural and semi-urban scenarios | M022 | R11 R12 | Facility staff and representative users scheduled; synthetic scenarios and feedback register ready. | Doctor | Not started |  | Pending |  |  |  |  | F041
M031 | 4 | SG4 | Doctor | 2 | Maternal/pediatric review of birth and loss flow | M027 M028 M029 | Stages 4–6 R04 | Maternal approval and facility pediatric review recorded separately; corrections assigned. | Team lead | Not started |  | Pending |  |  |  |  | F021, F023, F024, F025, F026, F027, F028
M032 | 4 | SG4 | Tester | 4 | Exercise twins, discharge, loss and transfer | M027 M028 M029 | AT15–AT18 AT29 | Run each sibling independently; verify pending and in-flight message behavior. | Tech lead | Not started |  | Pending |  |  |  |  | F021, F022, F023, F026, F027, F028, T015
M033 | 5 | SG5 | Tech lead | 5 | Review offline draft and child schedule boundaries | M025 | R05 R08 | Operation IDs, version conflicts and limited local data plan approved; no automatic clinical schedule selection. | Team lead | Not started |  | Pending |  |  |  |  | F029, F033, T016
M034 | 5 | SG5 | Tech lead | 3 | Review guardian and content withdrawal controls | M010 M018 | R02 R06 | Guardian authorization and withdrawal/cache invalidation contracts agreed; verification cases specified. | Pediatric reviewer | Not started |  | Pending |  |  |  |  | F032, F034, T010, T017
M035 | 5 | SG5 | Developer | 8 | Infancy and early-childhood workflows | M027 M033 | Stages 7–8 R03 R05 | AT19 pass; verified/outside/unknown dose history; no clinical interpretation; child tasks survive maternal closure. | Pediatric reviewer | Not started |  | Pending |  |  |  |  | F029, F030, F031
M036 | 5 | SG5 | Developer | 8 | Offline field drafts and reconciliation | M033 | R08 | AT20 pass; retries create one entry and conflicting plan changes cannot be overwritten. | Tech lead | Not started |  | Pending |  |  |  |  | F033, T016
M037 | 5 | SG5 | Developer | 6 | Guardian permissions and content publishing | M034 | R02 R06 | AT21 pass; approvals, text/audio versions, revoke and withdrawal paths work. | Tech lead | Not started |  | Pending |  |  |  |  | F022, F032, F034, T010, T017
M038 | 5 | SG5 | Team lead | 6 | Complete reviewed content production | M023 M031 | R06 | 12 topic packages in English and pilot language prepared; translation/narration resources confirmed. | Doctor | Not started |  | Pending |  |  |  |  | F020, F034, F035, T017
M039 | 5 | SG5 | Doctor | 2 | Review child schedules and content batch | M035 M038 | Stages 7–8 R05 R06 | Pediatric reviewer confirms child content; maternal reviewer confirms remaining maternal material. | Team lead | Not started |  | Pending |  |  |  |  | F029, F030, F031, F034, F035
M040 | 5 | SG5 | Tester | 6 | Test child access and weak-network drafts | M035 M036 M037 | AT19–AT21 AT29 | Low-end device evidence and unauthorized guardian/record checks recorded. | Tech lead | Not started |  | Pending |  |  |  |  | F029, F030, F031, F032, F033, T016
M041 | 6 | SG5 | Tech lead | 5 | Review security and complete requirement trace | M034 M037 | R01–R12 | All mandatory requirements mapped; evidence gaps and dependencies assigned. | Team lead | Not started |  | Pending |  |  |  |  | F040, T005, T019
M042 | 6 | SG5 | Tech lead | 5 | Prepare release infrastructure and recovery design | M002 M041 | R10 | Staging/production separation, migration/backup/restore and deployment plan ready; no deployment without approval. | Team lead | Not started |  | Pending |  |  |  |  | T020
M043 | 6 | SG5 | Developer | 7 | Rights requests, audit views and secure exports | M005 M037 | R07 | AT22 AT32 pass; scoped export, correction/deletion-review/grievance queue and minimal logs. | Tech lead | Not started |  | Pending |  |  |  |  | F025, F036, F037, T006, T009, T018
M044 | 6 | SG5 | Developer | 7 | Operational dashboard and reminder pause | M019 M020 | R10 R11 R12 | AT23 AT30 AT31 pass; backlog, failure queue, ownership, worker restart and cost counters visible. | Tech lead | Not started |  | Pending |  |  |  |  | F008, F024, F025, F038, F039, T012, T019
M045 | 6 | SG5 | Developer | 6 | Close end-to-end scope gaps and regressions | M035 M036 M043 M044 | Stages 1–8 R01–R12 | AT01–AT23 AT28–AT32 pass; full journey demo and content coverage complete. | Tech lead | Not started |  | Pending |  |  |  |  | F035, F040
M046 | 6 | SG5 | Team lead | 7 | Approve feature completeness and pilot operations draft | M041 M045 | R11 R12 | SG5 scope checklist; named support/backup; budget/rights/retention review owners; no silent cuts. | Doctor | Not started |  | Pending |  |  |  |  | F036, F038, F039, F042, T019, T020
M047 | 6 | SG5 | Doctor | 2 | Review complete journey and all content approvals | M039 M045 | R05 R06 R11 | 12 topic packages signed or blocked; clinical feedback retested. | Team lead | Not started |  | Pending |  |  |  |  | F034, F035, F040, T017
M048 | 6 | SG5 | Tester | 6 | Run complete functional acceptance suite | M045 | AT01–AT23 AT28–AT32 | Evidence at candidate SHA; all failures owned; critical/high defects block gate. | Tech lead | Not started |  | Pending |  |  |  |  | F036, F037, F038, F040, T018
M049 | 7 | SG6 | Tech lead | 5 | Run restore, rollback and load drills | M042 M045 | R10 R12 | AT25 AT26 pass with measured timings and agreed network/load profile. | Tester | Not started |  | Pending |  |  |  |  | T021, T022
M050 | 7 | SG6 | Tech lead | 4 | Review security and triage field findings | M041 M048 | R02 R07 R10 | No critical/high unresolved security defect; logging, secrets and permissions reviewed. | Team lead | Not started |  | Pending |  |  |  |  | T005
M051 | 7 | SG6 | Developer | 8 | Fix observed usability and reliability defects | M048 | R08 R12 | AT24 findings corrected and rerun on rural/semi-urban scenarios. | Tester | Not started |  | Pending |  |  |  |  | F041, T022
M052 | 7 | SG6 | Developer | 8 | Resolve regression and release hardening defects | M049 M050 | R10 | Recovery, stale content, message pause and access regressions retested. | Tech lead | Not started |  | Pending |  |  |  |  | T021
M053 | 7 | SG6 | Team lead | 8 | Conduct field sessions and operational rehearsal | M030 M046 | R11 R12 | At least 3 users/setting; outcome counts and support rehearsal; AT24 AT27 recorded. | Doctor | Not started |  | Pending |  |  |  |  | F014, F039, F041, F042, T022
M054 | 7 | SG6 | Doctor | 2 | Validate comprehension and clinical corrections | M051 M053 | R06 R11 R12 | No safety-critical misunderstanding; maternal and child issues resolved or gate held. | Team lead | Not started |  | Pending |  |  |  |  | F041, F042
M055 | 7 | SG6 | Tester | 8 | Independent field, resilience and regression verification | M049 M051 M052 | AT24–AT27 | Repeatable evidence; no reliance on author claims; risk-based regression recorded. | Tech lead | Not started |  | Pending |  |  |  |  | F041, F042, T021, T022
M056 | 8 | SG7 | Tech lead | 5 | Review candidate, migration and deploy rehearsal | M049 M052 | R10 R11 | Candidate SHA, reproducible release and restore/rollback check; approvals recorded. | Team lead | Not started |  | Pending |  |  |  |  | F043, T020, T021, T023
M057 | 8 | SG7 | Tech lead | 4 | Technical release review and bounded fixes | M055 M056 | R01–R12 | All mandatory evidence current; no critical/high defects; technical sign-off or hold. | Team lead | Not started |  | Pending |  |  |  |  | F043, T023
M058 | 8 | SG7 | Developer | 8 | Resolve release-candidate defects | M055 | R01–R12 | Assigned issues fixed and regression rerun; no new features. | Tech lead | Not started |  | Pending |  |  |  |  | F043, T023
M059 | 8 | SG7 | Developer | 8 | Package setup, training and final demonstration | M058 | R09 R11 | Fresh checkout instructions; release demo; support handover; candidate evidence pack. | Tester | Not started |  | Pending |  |  |  |  | F043, T007, T023
M060 | 8 | SG7 | Team lead | 8 | Obtain clinical, technical and operating sign-offs | M056 M057 M059 | R10 R11 R12 | Staffing, budget, contacts, vendor/privacy review and pilot go/no-go documented separately. | Doctor | Not started |  | Pending |  |  |  |  | F043, T023
M061 | 8 | SG7 | Doctor | 2 | Final maternal and pediatric clinical acceptance | M054 M059 | R05 R06 R11 | Signed content/plan versions and clinical acceptance for candidate or explicit hold. | Team lead | Not started |  | Pending |  |  |  |  | F043, T023
M062 | 8 | SG7 | Tester | 8 | Release acceptance and clean setup verification | M057 M059 | AT01–AT32 | Mandatory cases passed/current; independent evidence indexed; failed cases prevent sign-off. | Team lead | Not started |  | Pending |  |  |  |  | F043, T023

## Acceptance
MatriSathi acceptance scenarios
AT01–AT32 are this pack’s suite. Re-run affected cases at later gates and the release candidate.
Case | First gate | Requirements | Scenario | Test steps | Expected outcome | Reviewer | Result | Evidence link | Candidate SHA / date | Actual reviewer
AT01 | SG1 | R02 R07 | Staff login and sessions | Login with seeded staff; reject invalid/expired tokens; refresh, logout, replay and disable account. | Valid session works; rotated/revoked sessions fail; generic errors and throttling evidenced. | Tech lead | Pass | docs/delivery/evidence/SG1/report.md | 2026-09-30 (uncommitted working tree, pending commit)
AT02 | SG1 | R02 | Organization and facility isolation | Use two organizations, two facilities in one organization, coordinator and org admin; revoke membership. | Allowed access only; org admin cannot cross organization; same token loses revoked access. | Tech lead | Pass | docs/delivery/evidence/SG1/report.md | 2026-09-30 (uncommitted working tree, pending commit)
AT03 | SG1 | R02 | Shared phone and reference injection | Create two people sharing one phone; try linking an inaccessible Person into a new episode. | People remain distinct; forbidden link and unauthorized search denied without exposing records. | Tech lead | Pass | docs/delivery/evidence/SG1/report.md | 2026-09-30 (uncommitted working tree, pending commit)
AT04 | SG1 | R07 | Audit integrity | Create/read records; trigger denied request; try UPDATE/DELETE using runtime DB role. | Successful and denied events persist with actor/time; runtime cannot alter history; no sensitive payloads. | Tech lead | Pass | docs/delivery/evidence/SG1/report.md | 2026-09-30 (uncommitted working tree, pending commit)
AT05 | SG1 | R09 R10 | Repeatable foundation | Fresh checkout; locked install; migrations; real UI login/create/read; reload and restart. | Documented commands succeed; persisted record shown; CI output tied to SHA. | Tester | Blocked | docs/delivery/evidence/SG1/report.md | 2026-09-30 (uncommitted working tree, pending commit); CI not run — no remote (see report §6)
AT06 | SG2 | Stages 1–3 R05 | Late/unknown dating and schedules | Enter late pregnancy and unknown dates; clinician confirms/corrects dating; revise template. | Unknown stays unknown; only approved plan activates; past events retained; obsolete reminders cancelled. | Doctor | Not run
AT07 | SG2 | R03 | Appointments and overdue work | Request, confirm, miss, reschedule and cancel visit; assigned owner unavailable. | One clear next action; stale reminders cancelled; owned follow-up and backup; no inferred non-adherence. | Tester | Not run
AT08 | SG2 | Stage 2 R03 R07 | Reports and medicine records | Upload private report; record performed/received; unauthorized user tries clinical review. | Upload is not review; only clinician marks review; original prescription retained; ambiguous instructions queued. | Doctor | Not run
AT09 | SG2 | R03 | Referral closure | Record sent/contacted/attended/advice/follow-up; try closing only because message sent. | Closure follows defined state or reason; owner and unresolved work visible. | Doctor | Not run
AT10 | SG2 | Stage 3 R06 | Birth plan and urgent help | Open verified contact route without login/GPS; use web and printed plan. | Dated contact, alternate and direct dialler available; no dispatch/ETA or chat emergency promise. | Doctor | Not run
AT11 | SG3 | R01 | Real outbound messaging | Send approved template to consenting staff test handset; capture provider status callbacks. | Actual receipt verified; submitted/delivered/failed distinguished; no patient data in evidence. | Tech lead | Not run
AT12 | SG3 | R01 R10 | Retries and stale sends | Duplicate webhook/job; provider timeout; reschedule, opt out and restart worker. | No repeated effect; unknown delivery reconciled; send-time eligibility checked; failures owned. | Tech lead | Not run
AT13 | SG3 | R01 R02 | Inbound media and identity | Send real text/voice/photo; shared number ambiguous; unsupported/oversized upload. | Restricted unlinked queue; staff confirms identity; original audio playable; fallback and owner present. | Tester | Not run
AT14 | SG3 | R01 R06 | Audio and channel preferences | Play approved audio on web and permitted WhatsApp route; change language, safe timing, detail and opt-out. | Text equivalent visible; preferences honored; fallback works; no generated clinical answer. | Doctor | Not run
AT15 | SG4 | Stages 4–5 R02 | Birth and twins | Record birth with two children; update one child and leave other unchanged. | Distinct identities and histories; unknown facts allowed; siblings unaffected. | Pediatric reviewer | Not run
AT16 | SG4 | Stage 5 R04 | Separate discharge | Record mother and each child discharged on different dates with approved follow-up. | Each approval and instructions independent; no metric automatically clears discharge. | Doctor + Pediatric reviewer | Not run
AT17 | SG4 | R04 | Loss and message pause | Report loss while incompatible messages queued; confirm outcome; one twin affected. | Pause applies immediately to unsent incompatible messages; final send rechecks; in-flight limit logged; maternal support and sibling retained. | Doctor | Not run
AT18 | SG4 | R04 | Transfer and readmission | Transfer with open tasks and receiving owner; record readmission and original service dates. | Authorized sharing; no silent closure; handover accepted; historical dates/source preserved. | Doctor | Not run
AT19 | SG5 | Stages 7–8 R03 R05 | Child plans and vaccine records | Add unknown/outside dose; verify; clinician changes plan; close maternal episode. | No duplicate dose/reminder; raw measurements only; child work continues independently. | Pediatric reviewer | Not run
AT20 | SG5 | R08 | Offline and conflicts | Assigned worker drafts offline; newer online plan exists; retry sync; logout. | One visit per operation ID; conflict cannot overwrite clinical plan; visible pending/failed; local data cleared as designed. | Tech lead | Not run
AT21 | SG5 | R06 | Content governance | Review 12 topic packages; publish/withdraw one version; use previously cached public content. | Only approved versions newly distributed; text/audio and language match; cache expiry/withdrawal follows documented limits. | Doctor + Pediatric reviewer | Not run
AT22 | SG5 | R07 | Privacy and rights | Request correction/export/deletion review/grievance; try guessed file/record URL. | Owned request and response history; scoped export; no automatic clinical record deletion; unauthorized download denied. | Team lead + Tech lead | Not run
AT23 | SG5 | R10 R11 R12 | Operational dashboard | Create missed visit, failed message and overdue inbox case; worker unavailable. | Owner/backup, actionable failure queue, last-updated time, pause switch and administrative metrics visible. | Team lead | Not run
AT24 | SG6 | R08 R12 | Representative usability | Observe 3 rural and 3 semi-urban users including shared-phone/limited-literacy cases; next action/audio/help. | At least 5/6 succeed with intended assistance and no safety-critical misunderstanding; failures fixed/retested. | Tester + Doctor | Not run
AT25 | SG6 | R10 | Restore and rollback | Restore records/media/config in isolated staging; verify integrity; rehearse reversible release rollback. | Measured recovery meets approved RPO ≤24h/RTO ≤4h targets; audit and pending jobs reconciled without resend. | Tech lead | Not run
AT26 | SG6 | R12 | Load and weak network | Use 100 synthetic records, 10 concurrent staff, 200 scheduled messages/day; record network and run length. | Proposed p95 core non-media views ≤3s under agreed profile; no lost/duplicate jobs; weak network errors recover. | Tech lead + Tester | Not run
AT27 | SG6 | R11 | Support and stop rehearsal | Simulate after-hours request, absent worker, disclosure concern and message-delivery outage. | Named coordinator, backup, clinical contact and stop procedure work; hours/fallback visible. | Facility owner | Not run
AT28 | SG2 | R02 R07 | Patient/caregiver access | Confirm subject identity on shared phone; grant/revoke adult delegation; test another person on same handset. | Only authorized subject records; immediate revocation on next request; safe minimal notifications. | Tech lead | Not run
AT29 | SG4 | R02 R04 | Child with incomplete history | Register existing child without known pregnancy dates or episode; verify guardian authority. | No fabricated pregnancy/history; explicit mother/guardian links; unverified guardian cannot view child records. | Pediatric reviewer | Not run
AT30 | SG5 | R01 R10 | Durable job recovery | Restart API/worker mid-job; run two workers in test; cancel and retry job. | Durable ownership/leases, dedup and reconciliation; no process-local correctness dependency. | Tech lead | Not run
AT31 | SG5 | R09 | AI-disabled behavior | Disable all optional AI/provider features and execute core journeys and help routing. | Essential tasks, approved education and human routing still work; no scoring, diagnosis or medical interpretation. | Doctor + Tech lead | Not run
AT32 | SG5 | R07 R10 | Files, logs and exports | Test disallowed upload, signed-link expiry, spreadsheet-like input and sensitive log paths. | Validated private files; minimal logs; safe scoped export; no secrets or patient text in diagnostics. | Tech lead | Not run

## Capacity
Weekly capacity and estimates
Edit available hours to the confirmed commitment. Negative balance requires reassignment or a revised date.
Week | Role | Available h | Planned h | Remaining h | Action / decision
1 | Team lead | 10
1 | Tech lead | 10
1 | Developer | 25
1 | Doctor | 2
1 | Tester | 0
2 | Team lead | 10
2 | Tech lead | 10
2 | Developer | 25
2 | Doctor | 2
2 | Tester | 4
3 | Team lead | 10
3 | Tech lead | 10
3 | Developer | 25
3 | Doctor | 2
3 | Tester | 4
4 | Team lead | 10
4 | Tech lead | 10
4 | Developer | 25
4 | Doctor | 2
4 | Tester | 4
5 | Team lead | 10
5 | Tech lead | 10
5 | Developer | 25
5 | Doctor | 2
5 | Tester | 6
6 | Team lead | 10
6 | Tech lead | 10
6 | Developer | 25
6 | Doctor | 2
6 | Tester | 6
7 | Team lead | 10
7 | Tech lead | 10
7 | Developer | 25
7 | Doctor | 2
7 | Tester | 8
8 | Team lead | 10
8 | Tech lead | 10
8 | Developer | 25
8 | Doctor | 2
8 | Tester | 8
Eight-week total by role
Role | Available h | Planned h | Remaining h
Team lead
Tech lead
Developer
Doctor
Tester
Doctor time is fully allocated. Pediatric, language and live support capacity must be confirmed separately.

## Decisions
Decisions and dependencies
Resolve each item before its due gate; proposed direction is not an approval.
ID | Due gate | Owner | Decision needed | Proposed direction | Status | Decision / rationale | Approved by / date | Evidence link
D01 | SG0 | Team lead | Exact weekly hours and named owners | Use 10h lead, 10h tech, 25h developer planning baseline; confirm developer 20–25h allocation. | Open
D02 | SG0 | Team lead + Doctor | Pilot sites, language and reviewers | One rural and one semi-urban setting; English plus one selected local language; named pediatric reviewer. | Open
D03 | SG0 | Team lead | Shared repository policy and delegated authority | Adopt task branches, PR review and human commit/push approvals; select merge approver. | Open
D04 | SG1 | Tech lead | Auth/session, runtime and dependency versions | Password staff login; reviewed session design; pinned supported versions and current dependency review. | Open | PROPOSED (pending Tech Lead approval): password staff login; 15-min access token + 14-day rotating refresh with reuse detection; Python 3.12.14 pinned via uv.lock; Node 26.8.1 pinned via .nvmrc; all dependencies pinned exactly. See report §5 (M003 review evidence). |  | docs/delivery/evidence/SG1/report.md
D05 | SG2 | Doctor + Pediatric reviewer | Clinical templates and urgent wording | Approve source/version/local applicability; no universal schedule by resource tier. | Open
D06 | SG2 | Team lead + Tech lead | WhatsApp provider/account and budget | Compare current direct/provider costs, onboarding and media support; no vendor selected by this pack. | Open
D07 | SG2 | Tech lead + Team lead | Patient verification and caregiver mechanism | No phone-only household access; agree revocation and assisted flow before patient rollout. | Open
D08 | SG3 | Team lead | Language recording and testing capacity | Assign language-capable narrator/reviewer; tester 40h across plan; pediatric time separate from gynecologist 2h/week. | Open
D09 | SG5 | Team lead + Facility owner | Hosting, retention, vendor data flows and rights | Document review applicable to pilot date; India hosting is proposed policy, not legal certification. | Open
D10 | SG5 | Team lead + Tech lead | Recovery, load and operating cost thresholds | Approve proposed RPO/RTO and load targets; set monthly INR budget, alert and send-stop limits. | Open
D11 | SG6 | Facility owner + Team lead | Live support roster and response commitments | Name coordinator, backup and clinical escalation before any real enrolment. | Open
D12 | SG7 | Team lead + Doctor + Tech lead | Pilot authorization | Separate technical, clinical and operations acceptance; pilot deployment and real enrolment need explicit authorization. | Open

## Traceability
Requirements to build and test
Source: MatriSathi_Specifications_Updated.xlsx v2, 28 Sep 2026; standalone amendments in baseline §1.
Requirement | Required scope | Gates | Implementation tasks | Acceptance cases
Stage 1 | Pregnancy confirmation and entry | SG1 SG2 | M004–M006 M011 M013 | AT03 AT05 AT06
Stage 2 | Routine pregnancy care | SG2 | M011 M012 | AT06 AT07 AT08 AT09
Stage 3 | Delivery readiness | SG2 | M013 M015 | AT10
Stage 4 | Labour/birth documentation | SG4 | M027 M028 | AT15 AT18
Stage 5 | Separate discharge | SG4 | M027 M031 | AT16
Stage 6 | Early postpartum | SG4 | M029 M031 | AT16 AT17 AT18
Stage 7 | Infancy | SG5 | M035 M039 | AT19 AT29
Stage 8 | Early childhood | SG5 | M035 M039 | AT19 AT29
R01 | WhatsApp and voice | SG3 | M017–M024 | AT11 AT12 AT13 AT14
R02 | Identity and caregiver access | SG1 SG2 SG4 SG5 | M003 M005 M010 M025 M034 M037 | AT01 AT02 AT03 AT28 AT29
R03 | Tasks, tests and referrals | SG2 SG5 | M009 M011 M012 M044 | AT07 AT08 AT09 AT23
R04 | Loss, transfer and special care | SG4 | M026–M029 | AT15 AT16 AT17 AT18
R05 | Local schedules and field roles | SG2 SG5 | M011 M015 M033 M035 M039 | AT06 AT07 AT19
R06 | Education and language | SG3 SG5 | M021 M023 M037–M039 M047 | AT14 AT21 AT24
R07 | Privacy, audit and rights | SG1 SG5 SG7 | M003 M005 M043 M050 | AT04 AT22 AT28 AT32
R08 | Low-connectivity field use | SG5 SG6 | M033 M036 M040 M051 | AT20 AT24 AT26
R09 | Independent MVP architecture; amended | SG1 SG5 | M002–M006 M045 | AT05 AT31
R10 | Deployment, recovery and cost | SG3 SG6 SG7 | M017 M019 M042 M049 M056 | AT12 AT25 AT26 AT30 AT32
R11 | Staffed pilot and release gates | SG0 SG6 SG7 | M001 M046 M053 M060 | AT23 AT27
R12 | Pilot evidence and impact | SG5 SG6 SG7 | M044 M053 M055 M060 | AT23 AT24 AT26

## Functional Specs
MatriSathi functional requirements by gate
Version 1.1 ¦ Filter Gate for the required build scope. Existing task dates/hours remain unchanged. Named approvals are still required.
Gate is the first delivery/verification milestone; controls continue afterward. Open mechanisms and proposed targets need a Decisions tab record.
Sources: MatriSathi_Specifications_Updated.xlsx v2 + MatriSathi_Functional_Technical_Baseline.docx v1.0 (28 Sep 2026), including standalone amendments.
Spec ID | Gate | Day | Feature / screen | Users | Detailed functionality to build | Required data | Workflow rules and exceptions | Rural / semi-urban use | What to demonstrate | Linked task IDs | Acceptance cases | Delivery owner | Required approval / open decision | Source requirement
F001 | SG0 | 2 | Adopt scope and delivery rules | Team lead; tech lead; doctor | Confirm the eight care stages, shared requirements, pilot language, two settings, named reviewers and team hours. Record accepted versions and first-stage authorization. | Scope version; owner names; capacity; site/language; reviewer; approved stage; decision date. | Standalone application. Essential journeys work without AI. Clinical content needs named approval. Keep required scope; estimate changes are explicit. | Same essential care/privacy features for NGO/PHC and private sites. Billing automation is deferred. | SG0 decision record names owners, language, reviewer, capacity and accepted amendments. | M001 M002 | SG0 evidence | Team lead | D01 D02 D03; team lead accepts baseline. | Baseline §1, §9; R09–R12 as amended
F002 | SG1 | 7 | People and pregnancy registration | Coordinator; authorized patient; clinician | Find an authorized record or create a person, capture available intake and create a separate pregnancy episode. Save and reopen the same record after reload. | Person ID; episode ID; owning facility; name; available age/DOB with precision; history; existing medicines/allergies; source; available dates. | Keep missing history unknown. Do not infer normal findings, risk or diagnosis. No mandatory Aadhaar, ABHA, email or smartphone. Enforce authorized person linking. | Assisted entry for low-literacy/no-phone users; responsive self-entry where enabled. Available MCP records may be attached in SG2. | Register early, late and unknown-date cases; reopen persisted record; reject inaccessible person links. | M004 M005 M006 M008 | AT03 AT05; AT06 at SG2 | Developer | Doctor validates intake; tech lead approves identity design. | Stage 1; R02 R09; Baseline §2–3, §7
F003 | SG1 | 7 | Shared phones and contact changes | Patient; coordinator | Store contact separately from person identity. Confirm which person a contact relates to and record safe preferences. Review suspected duplicates manually. | Contact value; linked person; verification evidence/status; preferred language; contact owner; change actor/date. | A phone number may belong to several people. Never merge by number or transfer identity on number change. Uncertain identity cannot expose records. | Support shared family handsets and no-phone assisted contact. No household-wide access from possession of a number. | Two women with one number have independent records; number change does not grant another person access. | M003 M005 M006 | AT02 AT03 | Developer | Tech lead reviews reference and search permissions. | R02; Stage 1; Baseline §2, §7
F004 | SG1 | 7 | Staff roles and assigned records | Org admin; coordinator; ASHA; ANM/nurse; doctor | Admin manages authorized memberships. Staff sees only facilities and records permitted by role and assignment. Clinician-only actions are reserved for clinical users. | Organization; facility; staff membership; capabilities; assignment; active/revoked state; audit actor. | Admin role alone gives no clinical-record access. ASHA cannot approve a clinical plan or mark report review. Revocation affects subsequent requests. | Assign workers according to actual training, availability and equipment; no village-wide access assumption. | Compare doctor, field worker and admin views in two organizations; revoke membership and retry access. | M003 M005 M008 | AT01 AT02 AT03 AT04 | Developer | Doctor confirms field role boundaries; tech lead confirms enforcement. | R02 R05 R07; Baseline §2, §8
F005 | SG2 | 14 | Dating and local care plans | Doctor; authorized coordinator; patient | Record provisional dating and its source. Clinician confirms or corrects dating and activates a versioned local ANC plan with individual exceptions. Publish future care actions. | Episode; LMP/other dating if supplied; source/precision; confirmation; template/version; approver; effective date; individual dates. | Unknown dates stay unknown. Do not invent previous visits. Correcting dates preserves historical care and cancels/replaces obsolete future reminders. Resource tier does not select a clinical standard. | Works at first contact at any gestation. Only locally adopted schedules and actually available appointments are shown. | Late and unknown-date entry works; clinician changes date/plan; completed events stay intact and old reminders stop. | M009 M011 M015 | AT06 | Developer | D05; doctor approves actual schedule, sources and wording. | Stage 1–3; R05; Baseline §3, §5
F006 | SG2 | 14 | Patient next-action view | Patient; delegated caregiver; coordinator | Show the next confirmed action, date/location if known, preparation, status and help route. Let the person report done, not done or need help and request a callback. | Subject; approved action; due date/status; preparation version; contact; reported response; barrier; last update. | Keep patient-reported completion distinct from staff verification. Missing logs stay unknown. Do not infer non-adherence or clinical urgency. | Large controls and plain language. Staff can explain and print next steps; phone/assisted fallback when data is unavailable. | Patient identifies next action and help route; staff sees a help request with owner and context. | M011 M013 | AT07 AT10 AT28 | Developer | Doctor reviews preparation; team lead reviews usability. | Stages 1–3; R03 R06; Baseline §2–3
F007 | SG2 | 14 | Appointments and rescheduling | Patient; coordinator; clinic staff | Request an appointment, confirm actual date/site, record attendance or missed visit, and reschedule/cancel. Create an owned follow-up after a missed visit. | Appointment ID; subject; requested/confirmed time; facility/contact; status; prior appointment; owner; reason. | States: requested, confirmed, attended, missed, rescheduled, cancelled. Preserve old event; cancel obsolete reminders. Booking is a request until a person confirms. | No assumption of live hospital scheduling integration. Staff confirms local clinic/community availability manually. | Miss a visit, assign follow-up, reschedule once and show only the current reminder is eligible. | M009 M011 M016 | AT07 | Developer | Doctor and coordinator validate actual booking workflow. | Stage 2; R03 R05; Baseline §5
F008 | SG2 | 14 | Owned tasks and practical barriers | Coordinator; ASHA; ANM/nurse; patient | Assign follow-up, record due time, contact attempt and patient barriers, and close with result/reason. Reassign unavailable staff and overdue work to a backup. | Task type; subject; owner/backup; due time; state; attempt time; travel/cost/medicine-access barrier; closure reason. | States: new, assigned, awaiting patient, completed, cancelled. Declined, unreachable and unknown remain distinct outcomes. Overdue means administrative delay, not clinical risk. | No daily field visits or kit availability assumed. Use actual staff acceptance and facility fallback. | Unavailable worker and unreachable family both retain owned unresolved work; completion has recorded outcome. | M009 M011 M029 M044 | AT07 AT23 AT27 | Developer | Doctor validates role limits; facility confirms available owners. | R03 R05 R11; Baseline §5
F009 | SG2 | 14 | Investigations and report review | Patient; nurse; coordinator; clinician | Record requested tests, performed event, report receipt/upload and clinical review as separate steps. Route missing records and review work to named staff. | Test/request; request/performed/received dates; source; private file; reviewing clinician/date; next approved action. | Requested → performed → received → reviewed. A received outside report may have unknown earlier dates; retain them as unknown. Only an authorized clinician records review. No report interpretation. | Accept available paper/MCP photos or PDFs through staff-assisted upload; preserve originals. | Upload is displayed as received, not reviewed; non-clinician review attempt fails; clinician review is attributable. | M009 M012 M016 | AT08 AT32 | Developer | Doctor approves review workflow. | Stage 2; R03 R07; Baseline §3, §5
F010 | SG2 | 14 | Existing prescriptions and reminders | Patient; caregiver with grant; clinician; coordinator | Display an already issued prescription and set a reminder only from confirmed instructions. Route unclear medicine instructions to a clinician. | Original prescription/source/date; confirmed instruction; clinician/confirmation; reminder timing; start/end if supplied; pause. | Do not suggest drugs, calculate dose/duration or rewrite prescriptions. Keep changes and originals traceable. Uncertainty blocks the affected reminder until reviewed. | Support assisted reading and approved medicine-use education. Record availability/cost barriers as help requests. | Known instruction produces the agreed reminder; ambiguous instruction creates review work without invented dosing. | M012 M021 | AT08 AT12 AT14 | Developer | Doctor confirms instruction and patient wording. | Stage 2; R03 R06; Baseline §3, §7
F011 | SG2 | 14 | Referrals and return advice | Clinician; coordinator; receiving team | Record clinician-selected destination and urgency, contact the receiving service, track attendance and returned advice, and assign resulting follow-up. | Referral ID; subject; destination/contact; clinician instruction; receiving owner; sent/contacted/attended/advice dates; closure reason. | States: sent, contacted, attended, advice received, follow-up completed, or explicit closure reason. A message sent does not close the referral. No automatic specialist/risk matching. | Use verified local services, phone calls and manual external records; no hospital-system integration required. | Demonstrate missed attendance, return advice and open follow-up; close only with defined outcome/reason. | M012 M016 M028 | AT09 AT18 | Developer | Doctor validates referral destination/urgency and closure meaning. | Stages 2, 6–8; R03 R04; Baseline §5
F012 | SG2 | 14 | Raw observations and clinician findings | Authorized nurse; clinician; coordinator | Record available dated observations and source records; show measurement history and clinician-entered findings alongside the next approved action. | Observation name; raw value; unit; actual service date; entry date; source; recorder; clinician finding if supplied. | No threshold alerts, inferred high risk, fetal growth interpretation or automatic non-adherence. Preserve unknown values; correction records reason and prior value. | Only measurements actually taken with available equipment and trained staff are entered. | Enter a measurement and external finding; no generated judgment appears; date/unit/source remain visible. | M012 M015 | AT08 AT31 | Developer | Doctor approves allowed fields and units before use. | Stage 2; G07; R03 R05; Baseline §7
F013 | SG2 | 14 | Birth preparation plan | Patient/family; ASHA; coordinator; doctor | Capture chosen delivery site, clinician-selected referral site, companion, practical transport plan, landmarks and alternate contacts. Review changes with family and print/save the plan. | Site names; verified numbers; verification owner/date; alternate; landmarks; companion; transport arrangement; handover acceptance if known. | Manual confirmation only. No dispatch, ETA, GPS, geofence, cab booking or guarantee of transport suitability/availability. | Landmarks and printed plan work without location permissions. Verify locally applicable emergency numbers before publishing. | Open and print the plan; show dated primary/alternate contacts and an agreed fallback if transport unavailable. | M013 M015 | AT10 | Developer | Doctor approves clinical plan and urgent wording; coordinator verifies contacts. | Stage 3; R06; Baseline §3
F014 | SG2 | 14 | Public urgent help and service hours | Patient; family; staff | Provide approved urgent instructions and verified telephone routes without login. Open the dialler on supported devices. Explain messaging support hours and direct after-hours route. | Public approved instruction version; facility/alternate number; verification date/owner; support hours; response expectation. | Opening dialler is not proof of connection or dispatch. Do not suggest waiting for a chat reply in an emergency. No automated symptom triage. | Readable public text, reviewed audio when available, print and ordinary telephone fallback. No GPS/account dependency. | Signed-out user reaches the verified contact route; chat does not promise emergency monitoring. | M013 M015 M022 M053 | AT10 AT14 AT27 | Developer | Doctor approves urgent content; facility confirms actual hours before live use. | Stages 3–6; R06 R11; Baseline §2–3
F015 | SG2 | 14 | Patient access and adult delegation | Patient; caregiver; authorized verifier | Verify the subject through the agreed patient-access process. Grant limited adult caregiver permissions, show current grants and revoke access. Use safe sessions on shared devices. | Verified subject; verifier/evidence; grantor; caregiver; allowed records/actions; expiry/revocation; session. | Phone possession alone is insufficient. Check scope on each request and download; revocation takes effect on next request. No automatic disclosure of private concerns. | Assisted verification for no-phone users; family members on one handset remain separate. | Authorized caregiver sees granted records only; revoked caregiver and another phone-sharing person are denied. | M010 M013 M016 | AT28 AT02 AT32 | Developer | D07 must select concrete verification/recovery method; do not invent it. | R02 R07; Baseline §2, §8
F044 | SG2 | 14 | Verified local service contacts | Coordinator; ASHA; patient/family | Maintain locally verified PHC, referral, transport, nutrition and benefit contacts. Help the family contact a real service and record practical follow-up. | Service name/type; contact/alternate; locality/landmarks; verification owner/date; availability notes; referral/follow-up link. | No automatic eligibility, benefit claims, transport booking or government integration. Staff verifies availability and updates stale details. | Ordinary telephone calls and printed contacts work in both settings; never promise a free or available service without confirmation. | Find a local contact, identify its last verifier/date and create an owned follow-up when the service is unavailable. | M012 M013 M015 | AT09 AT10 AT07 | Developer | Facility verifies contacts; doctor approves clinical referral routes. | R03; Stage 3; Baseline §3, §5
F016 | SG3 | 21 | Channel and safe-contact preferences | Patient; coordinator | Record WhatsApp permission, preferred language, safe time and permitted message detail. Allow opt-out and callback request; show and enforce current preferences. | Subject/contact; permission status/time/source; language; safe time; detail level; opt-out; callback owner. | Recheck preferences before sending. Revocation/opt-out cancels ineligible pending messages. A channel opt-out does not erase medical records. | Minimal notifications on shared phones. Assisted or telephone contact remains available when WhatsApp is unsuitable. | Change safe timing and opt out with a queued reminder; affected message is not sent and fallback is visible. | M019 M021 M022 M007 | AT12 AT14 AT28 | Developer | Doctor reviews template wording; team lead approves provider setup. | R01 R02 R07; Baseline §2, §5
F017 | SG3 | 21 | Real WhatsApp reminders and delivery | Patient; coordinator | Send approved templates for confirmed actions through the official provider. Record status updates and expose failed/uncertain delivery for human follow-up. | Business operation ID; provider message ID; authorized recipient; template/language/version; plan version; send time; callback status. | Submitted/sent/delivered/failed/unknown are distinct. Delivery is not clinical review. Respect current approved provider rules; no blind resend after uncertain timeout. | Use permitted audio link/reply route. Ordinary call/assisted fallback for failure; no assumption of free messaging. | Actual template arrives on staff test handset; callbacks, duplicate events, stale schedule and failed delivery handled. | M014 M017 M019 M024 | AT11 AT12 | Developer | D06; real provider approval and budget required for SG3 pass. | R01 R10; Baseline §5, §8
F018 | SG3 | 21 | Human-owned text and voice inbox | Coordinator; nurse; clinician | Receive text/audio/photo into an authorized inbox. Staff identifies the subject, listens to original audio, assigns owner/backup, replies or routes to a clinician and records resolution. | Provider inbound ID; sender contact; verified subject if known; original media; owner/backup; state; timestamps; resolution. | States: new, being handled, awaiting patient, resolved. Ambiguous shared-phone messages remain restricted and unlinked. No transcription, AI clinical answer, triage or reassurance. | Human local-language handling. Callback route when staff cannot understand audio or identity remains uncertain. | Receive real voice/photo; hold ambiguous message; verify before linking; route a clinical question and show ownership. | M018 M020 M024 | AT13 AT23 AT27 | Developer | Facility assigns response owners; doctor confirms clinical routing. | R01 R02 R03 R11; Baseline §2, §5
F019 | SG3 | 21 | Media and unsupported-message fallback | Patient; coordinator | Play authorized original voice notes and view permitted photo/report files. Explain upload failure or unsupported type and offer a callback/assisted route. | Private file ID; MIME/type; size; source/provider ID; subject authorization; receipt status; failure reason; callback task. | Limits are explicit and provider-compatible. No public patient-media URLs. Failed upload must not look received. Verify access on every download. | Small files and clear progress/error status on weak networks; original audio does not require speech recognition. | Oversized/unsupported media yields understandable fallback; unauthorized download and expired link fail. | M018 M020 M021 | AT13 AT32 | Developer | Tech lead sets supported types, sizes and retention with facility review. | R01 R07 R08; Baseline §5, §8
F020 | SG3 | 21 | Reviewed audio and language access | Patient; family; staff | Play short approved education audio with matching text through patient pages and a permitted WhatsApp route. Offer English and the selected pilot language. | Topic; stage/plan match; text/audio version; language; source; approver; review date; file size. | Use reviewed human narration. No dialect recognition or conversational voice agent. Only approved clinical wording may be distributed. | Large play/pause controls, small files, plain text/picture support and printed next steps. | Play approved audio on web and real WhatsApp route; language/text agree; fallback usable on a low-end device. | M021 M023 M038 | AT14 AT21 AT24 | Developer | D08; language-capable reviewer and clinical reviewer approve versions. | R01 R06; Baseline §2, §5
F021 | SG4 | 28 | Labour arrival, birth and twins | Nurse; coordinator; doctor | Locate the correct episode, record arrival or transfer after care permits, record confirmed birth outcome and create a separate record/plan for each liveborn child. | Episode; arrival/event date and precision; source; confirmed outcome; distinct child IDs; actual birth date/time if known; facility summary. | No labour triage, contraction advice, resuscitation or live monitoring. Unknown facts stay unknown. Each child has independent outcome and follow-up. | No QR scan required to find the record. Manual facility summary and handover are sufficient. | Create twins and update one child; sibling and maternal history remain correct. | M025 M027 M031 M032 | AT15 | Developer | Doctor and pediatric reviewer approve birth/outcome workflow. | Stage 4; R02 R04; Baseline §3–4
F022 | SG4 | 28 | Child entry with incomplete history | Coordinator; guardian; pediatric reviewer | Create an existing child record even if pregnancy/parental details are incomplete. Verify guardian authority before access and link known relationships explicitly. | Child person ID; available birth date/precision; source; optional episode; verified relationships/guardian authority; owning facility. | No invented pregnancy, dates or parent identity. Unknown history is allowed; access still requires verified authority. Twins are separate people. | Assisted entry with available community or paper records; absence of digital identifiers is not a care barrier. | Register a child without an episode; unverified guardian sees no private record; later authorized linking preserves history. | M025 M027 M032 M037 | AT29 AT02 | Developer | Pediatric reviewer validates history/guardian workflow; D07 access design. | Stage 8; R02 R04; Baseline §4, §7
F023 | SG4 | 28 | Independent maternal/child discharge | Doctor; nurse; coordinator; family | Record clinician discharge decision for mother and each child separately. Attach approved instructions, existing prescriptions, teaching acknowledgement, contacts and individual follow-up. | Subject; clinical approver; actual discharge date; instructions/version; summary; follow-up; outstanding results; responsible clinician. | Administrative checklist never decides clinical readiness. No feeding/diaper metric unlocks discharge. Mother and twins may have different dates/facilities. | Print and reviewed audio for home care; practical follow-up is assigned only to available authorized staff. | Three different discharge dates for mother/twins; each retains correct instructions and next contact. | M027 M029 M031 M032 | AT16 | Developer | Doctor approves maternal decision; pediatric reviewer approves newborn workflow. | Stage 5; R04 R05; Baseline §4
F024 | SG4 | 28 | Postpartum and newborn follow-up | Mother; family; ASHA; nurse; clinician | Maintain separate maternal and newborn plans, scheduled home/clinic contacts and missed-contact follow-up. Record concerns and arrange available feeding/recovery support through usual care. | Subject plan; approved contact date/type; accepted worker; completion/source; concern; next task; referral. | No universal home-visit timetable or assumed equipment. No app-generated infection, jaundice, dehydration or mood score. Maternal unresolved needs continue beyond six weeks. | Allow clinic/phone/assisted contact based on real service availability; unavailable worker needs backup. | Miss a maternal contact while child contact completes; show independent follow-up and reassignment. | M029 M031 M044 | AT07 AT16 AT23 AT31 | Developer | Doctor/pediatric reviewer approves local PNC plans and role limits. | Stage 6; R03–R06; Baseline §4
F025 | SG4 | 28 | Private wellbeing and safety concerns | Patient; authorized coordinator; clinician | Provide a private concern/callback path for recovery, feeding, wellbeing, adolescent or safeguarding needs. Route only to authorized staff and record contact preferences. | Concern category/text or original voice; restricted subject; safe contact preference; assigned owner; referral/outcome. | No automatic caregiver disclosure or symptom interpretation. Do not promise continuous monitoring. Use approved direct urgent route outside staffed response. | Shared handset notification reveals minimal detail. Offer a safe telephone or in-person route where digital privacy is limited. | Caregiver cannot access a private concern; authorized staff receives it with owner and appropriate contact route. | M029 M031 M043 M044 | AT28 AT22 AT27 AT31 | Developer | Doctor/facility approves confidential routing and after-hours instructions. | Stage 6; R02 R07 R11; Baseline §2, §4
F026 | SG4 | 28 | Reported loss and immediate message pause | Authorized staff; doctor; pediatric reviewer | On reported loss, pause incompatible pending messages immediately; clinician later records confirmed outcome/source and appropriate follow-up. Preserve maternal support and unaffected sibling care. | Reported/confirmed outcome; subject/episode; report source/time; pause scope/reason; confirming clinician; retained follow-up. | Include miscarriage, termination, stillbirth and neonatal death sensitively. Final send rechecks pause. Already accepted provider messages may not be retractable; disclose in-flight limitation. | Human-assisted report is enough to initiate protective pause. Do not require a completed clinical record before pausing. | Pause queued routine/celebratory messages; confirm one twin outcome; other child and appropriate maternal tasks continue. | M026 M028 M031 M032 | AT17 AT12 | Developer | Doctor confirms outcomes and approved communication after loss. | R04; Baseline §4, §8
F027 | SG4 | 28 | Transfer and receiving handover | Coordinator; sending/receiving clinicians; family | Record movement to another facility/district or parental home. Share only authorized records, identify receiving owner, record acceptance and carry unresolved tasks forward. | Sending/receiving facility; sharing authority/scope; contact; receiving owner; acceptance; pending tasks; actual transfer date/source. | Changing facility does not close tasks or grant blanket cross-organization access. Mother and child can transfer separately. Pending acceptance stays visible. | Manual phone confirmation and agreed record handover; no receiving-system integration assumed. | Transfer with open results/referral tasks; receiving owner accepts; historical source/date and access remain correct. | M026 M028 M031 M032 | AT18 AT02 | Developer | Facility confirms sharing/acceptance procedure; doctor approves clinical handover. | R04; Stages 4–6; Baseline §4, §7
F028 | SG4 | 28 | Readmission and neonatal special care | Doctor; pediatric team; coordinator | Record clinician-supplied special-care/readmission event, attach available summary and update individual follow-up/receiving responsibility. | Subject; event date/source; care facility; supplied instructions; outstanding work; clinician; revised plan version. | Preserve prior birth/discharge history. No software inference of need for admission or special care. Do not replace sibling plans. | Document services actually available; arrange existing clinical support manually. | Readmit one child after discharge; earlier events remain and only affected future tasks change. | M028 M029 M031 M032 | AT18 AT16 | Developer | Maternal/pediatric reviewer approves relevant instructions. | Stages 5–6; R04; Baseline §4
F029 | SG5 | 42 | Vaccination plan and evidence | Parent/guardian; vaccinator; pediatric reviewer | Show clinician/vaccinator-approved planned dates. Record outside/reported doses, verify evidence and record administered doses. Update reminders after approved plan correction. | Child; vaccine/dose; planned and actual dates; provider; source/evidence; verification status/actor; plan version. | Planned, reported, verified administered and unknown are distinct. Do not calculate catch-up advice or let parent choose UIP/IAP clinical standard. Prevent duplicate dose/reminder effects. | Confirm community-session dates manually; accept MCP/official evidence. Export is a care record, not an official vaccine certificate. | Verify an outside dose; correct plan without duplicate record/reminder; unknown dose remains unknown. | M033 M035 M039 M040 | AT19 | Developer | Pediatric reviewer/vaccinator approves schedule and record fields. | Stage 7–8; R03 R05; Baseline §4
F030 | SG5 | 42 | Child measurements and community records | Authorized worker; nurse; pediatric reviewer | Record dated measurements, outside Anganwadi/community care and source evidence. Display factual history with open review appointments and referrals. | Child; observation/value/unit; actual service date; entry date; source; verification; attached evidence; review task. | No growth chart interpretation, malnutrition/developmental classification or automated screening. No government sync. Correction preserves original evidence/history. | Manual source-dated entry with available records/equipment; missing measurements remain unknown. | Outside service keeps actual date and source; raw measurements produce no classification. | M035 M039 M040 | AT19 AT31 | Developer | Pediatric reviewer approves units, fields and review process. | Stages 7–8; R03 R05; Baseline §4, §7
F031 | SG5 | 42 | Infancy and early-childhood continuity | Parent/guardian; coordinator; pediatric team | Provide child-specific next actions, review requests, approved food/hygiene/oral-care/safety/play guidance and tracked referrals from infancy through age five. | Child stage/date precision; approved review plan; concern; appointment; referral; source-dated community record; education version. | Review frequency comes from clinicians/programmes. Maternal episode closure does not end child work. Do not require annual-only visits or infer development from logs. | Same care features through WhatsApp/assisted and web channels based on capability. Local community sessions confirmed manually. | Close maternal episode and continue child appointments, guidance and referral follow-up. | M035 M039 M040 | AT19 AT29 AT31 | Developer | Pediatric reviewer approves stage guidance and local intervals. | Stages 7–8; R02 R03 R05; Baseline §4
F032 | SG5 | 42 | Guardian permissions lifecycle | Verified guardian; authorized staff | Verify legal/authorized relationship under the agreed process, grant scoped child access, update guardianship changes and revoke affected access. | Child; guardian person; authority evidence/status; verifier/date; permitted scope; grant/revocation; reason. | Relationship assertion or shared phone alone grants no access. Check authorization before every record/media request. Existing basic verification starts at SG4 child entry. | Offer staff-assisted verification using locally acceptable evidence and a documented exception path. | Wrong/unverified guardian denied; changed or revoked grant cannot retrieve child record/download. | M034 M037 M040 | AT29 AT28 AT22 | Developer | D07 plus facility/pediatric approval of verification process. | R02 R07; Baseline §2, §4
F033 | SG5 | 42 | Limited offline field visit drafts | Assigned field worker | On an approved device, save a permitted visit draft for an assigned caseload, show sync state, retry when online and resolve conflicts through an authorized person. | Operation ID; authorized subject; record version; draft fields; event date; local timestamp; sync state/error; last sync. | Drafts only, not a replicated medical record. Clinical-plan/discharge changes require online authorization. Retry creates one record; stale draft cannot overwrite newer plan. | Visible pending/failed/synced states on low-end phones. Paper/call fallback; protect/clear local data under agreed logout policy. | Disconnect, draft, change plan online, retry twice and log out; one visit saved and conflict stays visible. | M033 M036 M040 | AT20 AT24 | Developer | Tech lead approves allowed local fields/device and cleanup policy. | R08; Baseline §5
F034 | SG5 | 42 | Content publishing and withdrawal | Content editor; language reviewer; doctor; pediatric reviewer | Prepare text/audio version, record source and language review, obtain clinical approval, publish approved version and withdraw recalled material with reason. | Topic; stage; language; text/audio version; source; approver; review date; publish/withdraw status/time; expiry. | Initial approved playback starts at SG3. Only approved matching versions distribute. Withdrawal stops new sends and invalidates links; public cache expiry limits are documented. | Small public audio has text equivalent and contains no patient records. Reviewer checks understandable pilot-language narration. | Reject unapproved publish; publish approved version; withdraw and test old link, queued sends and cache behavior. | M034 M037 M038 M039 M047 | AT21 AT14 | Developer | Maternal/pediatric and language approvals required for their actual versions. | R06; Baseline §5
F035 | SG5 | 42 | Twelve education packages | Mother/family; doctor; pediatric reviewer | Complete packages for visit/test preparation, prescribed-medicine instructions, affordable nutrition, birth planning, urgent help, maternal recovery, feeding, newborn care, wellbeing, family planning, child play and vaccines. | For each topic: English and pilot-language text; short reviewed audio; source; version; clinician/language approver; review date. | Match confirmed stage/plan, not inferred disease. Education cannot prescribe treatment. All twelve packages required at SG5; early stage material reviewed incrementally. | Use affordable local examples, pictures where helpful, large audio controls and printed next steps. No blanket translation by unchecked AI. | Inventory twelve topics in both languages; play audio and inspect source/version/approval for maternal and child examples. | M038 M039 M045 M047 | AT21 AT14 AT24 | Team lead | Doctor/pediatric approval; named narrator/language reviewer under D08. | R06; Baseline §5
F036 | SG5 | 42 | Privacy notice and rights requests | Patient; coordinator; facility rights owner | Provide understandable notice/channel choices. Accept correction, record export, deletion-review and grievance requests; verify requester, assign owner, record decision and response. | Request type; subject/authority; received date; owner; progress; decision/reason; response; authorized export; audit reference. | No automatic deletion of required clinical records. Retention/lawful processing decided for actual pilot. Export only authorized records; ordinary logs exclude sensitive payloads. | Assisted/telephone request route for users unable to use web; private contact preferences respected. | Submit all four request types; trace owner/outcome; guessed file URL and unauthorized export fail. | M043 M046 M048 | AT22 AT32 | Developer | D09; facility/privacy review defines retention and handling policy. | R07; Baseline §5, §8
F037 | SG5 | 42 | Audit and correction visibility | Authorized reviewer; clinician; facility admin | Show attributable history of plans, outcomes, clinical review, sharing, overrides and reminder changes. Corrections preserve event date and prior history. | Actor; time; subject/entity; action; reason; prior/new version reference; actual event date; access scope. | Audit is protected from routine editing/deletion; privileged maintenance is controlled. Do not expose all clinical data to admins through audit views. | Authorized staff can explain who changed a plan without needing server access. Sensitive text/media stays outside general logs. | Review a corrected date, revoked grant and paused reminder with actor/reason; unauthorized audit access denied. | M005 M043 M048 | AT04 AT22 AT32 | Developer | Tech lead approves access and audit integrity. | R07; Baseline §7–8
F038 | SG5 | 42 | Operational worklist and pause controls | Coordinator; backup; facility/team lead | Show overdue tasks, missed visits, unreviewed reports, open referrals, pending inbox and failed/uncertain sends. Assign/reassign work and pause affected automation with reason. | Facility; owner/backup; due age; state; last update; provider status; failure reason; pause scope; actor/time. | Administrative priorities only. Show visible data freshness. Resume requires authorized review of current eligibility; do not bulk-resend stale jobs. | Bounded worklists suit busy clinics; phone follow-up remains possible during channel outage. | Create several unresolved cases, reassign unavailable owner, pause sending and demonstrate owned failure resolution. | M044 M046 M048 | AT23 AT30 AT27 | Developer | Facility agrees roster and ownership; tech lead confirms pause permissions. | R03 R10 R11; Baseline §5, §8
F039 | SG5 | 42 | Pilot impact and cost evidence | Team lead; facility owner | Show defined administrative measures and capture baseline/weekly observations: missed-visit follow-up, report-review time, referral closure, message failures/cost and staff time per request. | Metric definition; observation window; numerator/denominator; timestamp basis; baseline; cost source/currency; staff time sample. | Missing data is unknown, not zero. No clinical outcome claim from small POC. Distinguish delivered messages from reviewed requests and closed referrals. | Compare operational results by setting without ranking patients or assigning clinical standards by tier. | Trace sample metrics back to source events and explain baseline/denominator and cost coverage. | M044 M046 M053 | AT23 AT26 AT27 | Developer | D10; team lead approves metric definitions, budget and thresholds. | R12; Baseline §8–9
F040 | SG5 | 42 | Assistive scope and human override | All roles | Run complete care journeys with AI disabled. Route clinical questions to qualified people; allow authorized correction, pause, reassignment and override with a reason/audit. | Approved content/plan versions; human decision; override scope/reason; audit; assigned clinical route. | No diagnosis, treatment recommendations, clinical scoring, screening or medical-data interpretation. No autonomous clinical advice, generative FAQ/transcription or growth interpretation in MVP. | Core work must function through web/assisted care when optional AI or channel service is unavailable. | Execute maternal and child paths with optional AI off; verify all clinical outcomes come from approved content or human entry. | M041 M045 M047 M048 | AT31 | Developer | Doctor/pediatric review scope; tech lead verifies dependencies. | MVP boundary; R09 amended; Baseline §1, §9
F041 | SG6 | 49 | Rural and semi-urban usability | Tester; representative families; doctor | Observe next-action, audio and help tasks with at least three participants per setting, including shared-phone and limited-literacy use. Record assistance, misunderstanding and fixes. | Scenario/device/network; participant category without identifiers; task outcome; assistance; feedback; defect/retest. | Proposed gate: at least 5/6 succeed with intended assistance and none has a safety-critical misunderstanding. Use synthetic records; do not claim clinical benefit. | Test low-end phones, weak data, large text, audio controls and no-phone assisted/print route. | Observed outcomes and retests meet agreed gate; critical misunderstanding is corrected before release. | M051 M053 M054 M055 M030 | AT24 AT26 | Tester | Doctor validates comprehension; team lead accepts setting coverage. | R08 R12; Baseline §8
F042 | SG6 | 49 | Staffed support and stop rehearsal | Facility owner; coordinator; backup; clinical contact | Name live support/backup, response hours and urgent escalation. Rehearse after-hours, absent staff, disclosure concern and channel outage. Stop enrolment/affected automation when needed. | Roster; hours; response commitment; contacts/verification; escalation owner; stop/resume authority; incident record. | Doctor advisory 2h/week is not inbox coverage. Staffing must exist before first patient. One rural and one semi-urban site, up to ten families each only if staffing supports it. | Ordinary verified phone/in-person fallback; no promise of 24/7 app monitoring or ambulance integration. | Backup takes an unowned request; public hours/contacts correct; authorized person can stop enrolment/sending. | M046 M053 M054 M055 | AT27 AT23 | Team lead | D11; facility approves actual roster and response commitments. | R11; Baseline §2, §8–9
F043 | SG7 | 56 | Pilot release and training | Team lead; tech lead; doctor; pediatric reviewer; tester | Demonstrate complete journey, train staff, package setup/support instructions and obtain separate technical, clinical and operating decisions for the candidate release. | Candidate SHA; baseline versions; test evidence; clinical approvals; training record; support/recovery plan; defects; go/no-go. | All required stages/shared functions and AT01–AT32 evidenced. Critical/high defects block. Deployment and patient enrolment need authorization; Day 57–60 reserve is for corrections. | Train on real rural/semi-urban workflows, shared phones, manual fallback and loss/transfer cases. | Fresh setup and full acceptance pass; three sign-offs identify candidate and approved pilot boundaries. | M056 M057 M058 M059 M060 M061 M062 | AT01–AT32 | Team lead | D12; separate clinical, technical and operating sign-offs. | R10 R11 R12; Baseline §9; Delivery plan SG7

## Technical Specs
MatriSathi technical build specifications by gate
Version 1.1 ¦ Filter Gate for the required build scope. Existing task dates/hours remain unchanged. Named approvals are still required.
Gate is the first delivery/verification milestone; controls continue afterward. Open mechanisms and proposed targets need a Decisions tab record.
Sources: MatriSathi_Specifications_Updated.xlsx v2 + MatriSathi_Functional_Technical_Baseline.docx v1.0 (28 Sep 2026), including standalone amendments.
Spec ID | Gate | Day | Component / area | Implementation requirement | Data / interface contract | Controls and constraints | Failure / exception behavior | Verification required | Linked task IDs | Acceptance cases | Delivery owner | Required decision / approval | Source requirement
T001 | SG0 | 2 | Architecture and repository boundary | Adopt one standalone responsive frontend/backend path and bounded stage delivery. Essential functionality has no dependency on optional AI. | Proposed React/Vite/TypeScript; FastAPI modular backend; PostgreSQL/Alembic; private object storage; durable worker. Confirm at SG0/SG1. | Work only in current repository. No other-platform schema, authentication, code or brand dependency. No native app, microservice fleet or websocket requirement. | If the persisted first slice cannot be proved by SG1, record capacity/date impact rather than silently changing scope. | Approved architecture record and SG1 real browser persistence proof. | M001 M002 M004 M006 | AT05 AT31 | Tech lead | D01 D03 D04; stack is a proposed baseline until adopted. | R09 amended; Baseline §1, §6
T002 | SG1 | 7 | API contracts and validation | Version APIs and agree request/response schemas before dependent frontend/backend work. | /api/v1; OpenAPI; consistent error shapes; paging; bounded queries; operation IDs for retryable creates/uploads/effects; entity version on updates. | Derive organization/facility from current server permissions; never trust client subject/reference IDs. Separate clinical event date from entry time. | Reject invalid references/versions with actionable errors that do not leak inaccessible record existence. | Contract tests cover rejected cross-scope references, pagination and correct persisted response. | M003 M004 M005 M009 | AT02 AT03 AT05 | Tech lead | D04; tech lead approves concrete contracts by task. | R02 R09; Baseline §6–7
T003 | SG1 | 7 | Core schema and invariants | Create only first-slice tables initially; add later entities in their assigned stages using reviewed migrations. | Organization; Facility(org); StaffUser; Membership; Session; Person; ContactMethod; PregnancyEpisode(mother, facility, dating/source, status). Stable IDs; created/updated/version. | Validate ownership/sharing and foreign keys. Phone is not unique person identity. Use explicit unknown/precision; do not substitute zero, today or assumed normal. | Reject inaccessible person linking. Keep corrected history and original service/source information. | Migration from empty DB works; two people share phone; wrong-person reference fails. | M003 M004 M005 | AT02 AT03 AT05 | Developer | Tech lead approves Person ownership and migration invariants. | R02 R09; Baseline §7
T004 | SG1 | 7 | Staff authentication and sessions | Implement staff login, refresh, logout, expiry, account disable and replay handling. | Unique login; reviewed password hash; short access session; rotated refresh/token identifiers; expiry/revocation/lineage; current membership. | Generic authentication errors; bounded throttling; no production seed credentials. Document browser token storage, cookie/CSRF protections as applicable. | Logout, disabled user, revoked membership and refresh replay invalidate subsequent access; no process-local membership cache as authority. | AT01 with real DB/session behavior plus current-membership enforcement in AT02. | M003 M005 | AT01 AT02 | Developer | D04 fixes mechanism, lifetimes and supported versions before build. | R02 R07; Baseline §8
T005 | SG1 | 7 | Authorization and database roles | Enforce organization, facility, role and subject scope on every read/write/search/link/file/export. | Central authorization checks plus relational constraints; separate migration-owner and restricted runtime DB credentials. | No automatic clinical access from admin title. Enforce clinical-only actions and record grants. Denied logs survive business transaction rollback. | Reject guessed IDs and cross-organization references without exposing record existence. Runtime cannot edit/delete audit history. | Direct API/search/reference and DB-role tests; membership revoke uses same existing token. | M003 M005 M010 M018 M041 M050 | AT02 AT03 AT04 AT28 AT32 | Developer | Tech lead reviews sensitive access changes independently. | R02 R07; Baseline §2, §7–8
T006 | SG1 | 7 | Audit foundation and safe diagnostics | Capture successful/denied access and important state changes with minimal attributable metadata. | Actor; UTC system time; entity/action; scoped reference; reason; version/request ID. Clinical event time is separate. | No patient text, voice, phone numbers, secrets or identifiers in ordinary diagnostics. Restricted audit access; routine users cannot change history. | Audit for denied operation survives rollback. Privileged maintenance is explicitly controlled; do not claim absolute immutability. | Exercise denial, success, runtime UPDATE/DELETE and sensitive error path. | M003 M005 M043 | AT04 AT32 | Developer | Tech lead approves fields, access and retention with D09. | R07; Baseline §8
T007 | SG1 | 7 | Reproducible setup and CI | Create locked installs, documented local setup, test fixtures and CI for reviewed shared work. | Pinned supported runtimes/dependencies; PostgreSQL-backed tests; Python lint/type/tests; frontend lint/type/build; browser smoke; empty-DB migration; secret/dependency checks. | Synthetic development data only. Separate contributor checkouts/task branches; required review/CI or documented manual equivalent. Existing approval policy applies. | Failed checks prevent task acceptance; list checks not run. Do not weaken tests to make CI pass. | Fresh checkout runs documented commands and real persisted UI journey; evidence tied to SHA. | M002 M004 M006 M059 | AT05 | Developer | D03 D04; commits/pushes follow recorded human authority. | R09 R10; Baseline §9; Delivery plan §5
T008 | SG2 | 14 | Plans, typed work and state transitions | Implement distinct clinical-plan, appointment, task, investigation and referral state rules with current owner/version. | Plan(template version, approver, effective date, exceptions); Task(owner, due, state, reason); Appointment; Investigation; Referral; original files/events. | Validate each transition and role. Clinical plan activation/review belongs to clinician. Administrative urgency must not become clinical risk scoring. | Dating/reschedule correction preserves history and cancels superseded future actions/reminders atomically with durable intent as applicable. | Exercise late dates, missed appointments, upload-not-review, referral closure and stale reminder cancellation. | M009 M011 M012 | AT06 AT07 AT08 AT09 | Developer | D05; doctor approves schedule semantics and clinical-only transitions. | R03 R05; Baseline §5–7
T009 | SG2 | 14 | Private uploads and downloads | Store files privately with authenticated, subject-scoped access and clear upload/receipt states. | File ID; organization/subject; source; type; size; validated object key; checksum where used; upload status; authorized short-lived download. | Validate content/type/size; safe filenames; no public record bucket or long-lived public clinical URL. Shared-phone links need subject authorization. | Unsupported/failed upload remains failed with fallback; expired/revoked/unauthorized downloads fail. | Report/media upload plus guessed ID, expired link and unsupported-type tests. | M009 M012 M018 M020 M043 | AT08 AT13 AT22 AT32 | Developer | Tech lead chooses reviewed file limits and access mechanism. | R01 R07; Baseline §8
T010 | SG2 | 14 | Patient and delegated access contract | Specify identity verification, recovery, session and grant behavior before building patient access. | Person/subject session; verifier/evidence; CaregiverGrant(subject, grantee, scope, grantor, expiry, revocation); child authority extends at SG4/SG5. | Phone possession is not authorization. Verify current grant on record, search and download; protect shared-device sessions. | Ambiguous identity stays restricted. Number changes never silently transfer access. Revocation denies next authorized request. | Two women/one phone, another handset user, caregiver revoke and unverified guardian tests. | M010 M013 M034 M037 | AT28 AT29 AT22 | Tech lead | D07 is a blocking design decision; mechanism not pre-approved. | R02 R07; Baseline §2, §7–8
T011 | SG3 | 21 | Provider adapter and authenticated callbacks | Use one official WhatsApp provider behind an adapter; verify current rules during setup. | Outbound template send; provider IDs/status mapping; signature-verified webhook; inbound text/audio/photo; normalized status and error events. | Keep credentials server-side; validate callback signature and deduplicate provider event IDs. Restrict unlinked media/message queue. | Out-of-order/duplicate callbacks cannot create duplicate business effects or regress terminal status incorrectly; uncertain delivery requires reconciliation. | Real test handset receipt and real inbound media; reject invalid webhook; replay callback without duplicate work. | M017 M018 M019 M020 M024 | AT11 AT12 AT13 | Developer | D06; provider onboarding, template approval and media rules verified. | R01 R10; Baseline §5, §8
T012 | SG3 | 21 | Durable jobs and send eligibility | Persist intent with business change and process with durable claims/leases, bounded retries and an owned failure queue. | Job/outbox ID; operation key; subject/recipient; content/plan version; eligibility; scheduled time; lease; attempts; provider ID; terminal reason. | Before sending recheck current permission, recipient, plan, content and pause. Correctness cannot depend on in-memory jobs or counters. | Worker crash/retry cannot repeat effect. Unknown provider acceptance is reconciled rather than blind resend. Cancel obsolete intent; retain audit/failure owner. | Duplicate callback/job, timeout and worker restart tests at SG3; two-worker/crash suite at SG5. | M017 M019 M044 | AT12 AT30 | Developer | Tech lead approves retry/lease/timeout/reconciliation policy. | R01 R10; Baseline §6, §8
T013 | SG3 | 21 | Messaging privacy and operating limits | Apply safe timing/detail/language and channel opt-out consistently to outbound jobs and staff responses. | Contact preference/version; template/language/content version; consent state; send eligibility result; failure/callback owner. | No sensitive payloads in logs or evidence. Voice/media stays private. Provider delivery and clinician review are separate states. | Unsupported media or opt-out routes to appropriate human fallback. Never promise 24/7 monitoring through automated acknowledgement. | Queued opt-out, safe-time change, ambiguous sender, log redaction and denied media access. | M018 M020 M021 M022 | AT13 AT14 AT28 AT32 | Developer | Doctor approves patient wording; facility approves staffed response hours. | R01 R02 R07 R11; Baseline §2, §5
T014 | SG4 | 28 | Birth, child and event data integrity | Add child relationships and subject-specific outcome/discharge/readmission events without a mandatory fabricated pregnancy. | Child with Person ID; optional known episode; explicit mother/guardian relationships; per-subject birth/outcome/discharge/transfer events; source and date precision. | If a record can target episode or child, require exactly one valid subject with correct scope. Separate child and maternal lifecycle. | Updating one twin must not affect sibling; unknown dates remain unknown; readmission never erases prior discharge. | Twins, independent discharge, existing child without episode and wrong-subject link tests. | M025 M027 M029 | AT15 AT16 AT29 | Developer | Doctor/pediatric reviewer approves event meaning; tech lead reviews constraints. | R02 R04; Baseline §4, §7
T015 | SG4 | 28 | Loss pause and transfer consistency | Make reported-loss pause and handover changes safe under concurrent workers and user updates. | Subject-scoped pause/reason/version; final send check; outcome confirmation; transfer scope; receiving owner/acceptance; pending tasks. | Pause is protective before confirmation. Preserve appropriate maternal/sibling work. Sharing must be authorized, not inferred from new facility. | Record in-flight provider limit. No silent closure on transfer; concurrent edits use versions/transaction boundaries and require reconciliation. | Queue/claim/pause race; one-twin loss; mother/child transfer to different sites; pending receiving acceptance. | M026 M028 M032 | AT17 AT18 AT12 | Developer | Doctor approves outcome communication; tech lead approves concurrency design. | R04 R10; Baseline §4, §8
T016 | SG5 | 42 | Offline drafts and sync contract | Limit offline storage and changes to approved visit drafts for assigned caseloads on approved devices. | Operation ID; subject authorization; base record version; allowed payload; event/source date; pending/failed/synced state; conflict response. | No offline clinical-plan/discharge approval. Recheck current authorization at sync. Define local storage, retention and logout cleanup without losing unsent work silently. | Retry is idempotent; stale version never overwrites current clinical plan. Show conflicts and pending drafts for authorized resolution. | Offline draft, online change, repeated sync, revoked worker, logout/cleanup and weak-device tests. | M033 M036 M040 | AT20 AT24 | Developer | Tech lead approves device/local data rules and conflict UX. | R08; Baseline §5
T017 | SG5 | 42 | Content lifecycle and cache control | Store approved matching text/audio versions and prevent new distribution of withdrawn or expired content. | Content topic/stage/language/version; source; approver/review date; publish/withdraw state; public-cache expiry; link version. | Only public education may be cached under policy; patient records excluded. Recheck current eligibility when scheduled content sends. | Invalidate withdrawn links/queued messages. Offline public copies may persist until approved expiry; document limit and refresh indication. | Withdraw version, follow old link and test previously cached public audio under stated expiry policy. | M034 M037 M038 M047 | AT21 AT14 | Developer | Clinical/language review plus tech lead-approved expiry and invalidation. | R06 R08; Baseline §5
T018 | SG5 | 42 | Rights, exports and audit views | Implement scoped request workflow, safe care-record exports and authorized audit inspection. | Rights request(type, subject, authority, owner, status, outcome); export scope; audit filters; retention review decision. | Neutralize spreadsheet formula-like user input in exports; authorized downloads only. No automatic clinical record deletion or public vaccine certificate claim. | Revocation/expiry blocks export retrieval; logging avoids sensitive values; request failures retain owner and visible state. | Correction/export/deletion-review/grievance cases; guessed file; formula-like cell; sensitive logs. | M043 M048 | AT22 AT32 AT04 | Developer | D09; facility determines retention/legal basis before live use. | R07 R10; Baseline §5, §8
T019 | SG5 | 42 | Operations, observability and cost | Provide actionable queue/health metrics, last update, pause controls and reviewed cost limits. | Backlog by type/owner; job/failure/uncertain states; worker health; restricted logs; provider cost source; INR budget/alert/stop limits; audit. | Metrics are administrative. Define denominator/time basis. Restrict bulk pause/resume; no process-local correctness. Use bounded queries and pagination. | Alert assigned operator for stopped worker/failures; no false success on failed record receipt. Cost stop prevents further affected sends and leaves owned work. | Queue, restart, duplicate-effect, stale-data and cost-control rehearsal with synthetic events. | M041 M044 M046 | AT23 AT30 AT31 | Developer | D10 selects thresholds/budget; facility owns operational response. | R10 R11 R12; Baseline §8
T020 | SG5 | 42 | Release configuration and vendor review | Prepare separate local/staging/production configuration, secret handling, deployment steps and vendor/data-flow review. | Environment config; secret references; migration version; dependency locks; object store; worker config; backup plan; vendor inventory. | No real patient data in development/CI/evidence. Encryption in transit/at rest; restricted access. Hosting location is a policy decision, not a legal certification. | Record service-unavailable fallback; deployments need authorization. Privacy/retention/vendor gaps block live enrolment. | Document reviewed configuration and reproducible release procedure; later recovery drill proves operability. | M042 M046 M056 | AT05 AT25 AT32 | Tech lead | D09 D10; applicable pilot-date review and cost approval. | R07 R10; Baseline §8
T021 | SG6 | 49 | Backup, restore and rollback | Restore records, media and necessary configuration in isolated staging and reconcile audit/pending jobs. Rehearse application and migration-compatible rollback. | Backup timestamps; source versions; integrity checks; restore start/end; pending jobs/provider acceptance; rollback steps; operator. | Proposed RPO ≤24h and RTO ≤4h need approval and measured proof. Protect backups and secrets. Do not assume code rollback reverses destructive schema changes. | Recovery must not resend provider-accepted messages or lose pending ownership. Failed drill blocks release until corrected. | Timed restore and rollback with integrity, access, audit and message reconciliation evidence. | M049 M052 M055 M056 | AT25 | Tech lead | D10 approves targets; tester independently records drill evidence. | R10; Baseline §8
T022 | SG6 | 49 | Load, weak network and accessibility | Test the agreed pilot profile and actual low-end devices; measure errors as well as latency. | 100 synthetic records; 10 concurrent staff; 200 scheduled messages/day; recorded network/run duration; p95 core non-media latency; retry/duplicate counts. | Proposed p95 ≤3 seconds under agreed network. Media tested separately. Targets are project assumptions, not certification of future scale. | Weak-network failures show pending/error and recover without duplicate effects. Large text/audio/help tasks remain usable. | AT26 measured run plus six-user AT24 evidence; document conditions, defects and retests. | M049 M051 M053 M055 | AT24 AT26 | Tech lead | D10 and tester approve profile; doctor assesses comprehension. | R08 R12; Baseline §8
T023 | SG7 | 56 | Release evidence and change control | Tie mandatory tests, content approvals, setup and operational sign-offs to one candidate SHA. | Baseline/version; M/F/T/AT mapping; CI and demo evidence; doctor feedback; open defects; reviewer; release/rollback plan; authorization. | No critical/high open defects. No gate auto-passes from task counts. Evidence reuse requires affected-code assessment. Keep patient data/secrets out of reports. | Failed mandatory check holds affected release. Days 57–60 are correction reserve; new features need re-estimation. | Fresh setup, all AT01–AT32 current, independent review and separate technical/clinical/operating sign-offs. | M056 M057 M058 M059 M060 M061 M062 | AT01–AT32 | Tech lead | D12; team authorizes deployment/enrolment separately. | R10–R12; Baseline §9; Delivery plan SG7